## Cover
An illustration of the application of Failure Modes and Effects Analysis (FMEA) techniques to the analysis of information security risks
Introduction and acknowledgement
The original version of this spreadsheet was kindly provided to the ISO27k Implementers' Forum by Bala Ramanan to demonstrate how the FMEA method can be used to analyze information security risks. Subsequently, Bala kindly agreed to donate it to the ISO27k Toolkit. Apart from minor updates and reformatting, it is essentially unchanged. We are very grateful for Bala's input.
Contents
The FMEA Sample tab has the actual illustration - an analysis of possible failure modes for a firewall.
The Guidelines provide additional notes on the FMEA method, including a step-by-step process outline.
The Severity, Probability and Detectability tabs have tables demonstrating scales commonly used to rank risks by these criteria.
Copyright
This work is copyright © 2008, ISO27k Forum, some rights reserved. It is licensed under the Creative Commons Attribution-Noncommercial-Share Alike 3.0 License. You are welcome to reproduce, circulate, use and create derivative works from this provided that (a) it is not sold or incorporated into a commercial product, (b) it is properly attributed to the ISO27k Implementers’ Forum at www.ISO27001security.com, and (c) derivative works are shared under the same terms as this.
Disclaimer
Risk analysis is more art than science. Don't be fooled by the numbers and formulae: the results are heavily influenced by the accuracy of the users' assessment of risk factors, by the definition of information assets and by the framing of risks being considered. For these reasons, the process is best conducted by a team of people with solid expertise and practical experience of (a) assessing and managing information security risks, and (b) the organization, its internal and external situation with respect to information security. Don't expect to get definitive answers from anyone. It is impossible to guarantee that all risks have been considered and analyzed correctly. Some very experienced practitioners in this field claim that all risk analysis is basically bunkum, and we have some sympathy with that viewpoint.
The results of the analysis should certainly be reviewed by management (ideally including IT auditors, Legal, HR, other support functions and/or information security consultants) and may be adjusted according to their experience, so long as the expert views are taken into consideration. Remember: just because the organization has little if any experience of a particular informaiton security risk does not necessarily mean that it can be discounted. Organizations with immature security management processes and systems may have significant ongoing security incidents that are not even recognized, due to inadequate incident detection and reporting processes.

## Guidelines
Guideline to Carry out a Risk Assessment Using FMEA
Important notes:
This method does not consider asset values. Rrisks are identified for each asset and prioritized without taking account of the asset values.
The Cumulative risk for the identified asset for each threat is ascertained by the Risk Priority Number (RPN)
Each asset can have more than one failure mode and for each failure mode there can be more than one vulnerability
How to carry out the Risk Assessment (RA) using FMEA:
1 | Identify the assets or the services rendered by the department under the scope of RA
5 | Now identify the failure modes for the identified asset/function. Please note that there could be more than one vulnerabilities for each asset
6 | Now identify the impact if the identified failure mode happens. That if the identified failure mode happens what will be the effect on the business or service.
7 | Now refer the impact chart and choose the number relevant to the effect of the failure mode
8 | Now identfiy the cause for the failure mode. Please note that each vulnerability can be linked with more than one threat.
9 | Now refer to the probability chart and choose the number that is more relevant to the frequency of the threat happening.
10 | Now list down the current controls. Kindly categorize the controls as preventive and detective controls. Write each control in separate rows.
11 | Now refer to the vulnerability chart and choose a number relevant to the size of vulnerability for each asset and the effectiveness of the controls that might have.
12 | Input all three in the corresponding fields. You can now see the Risk Priority Number calculated for a failure mode of the respective asset function.
13 | Now if the RPN is not under the acceptable value then the risk status shows "HIGH RISK", recommendation to mitigate each of these HIGH RISK has to be listed down. Kinldy list each control in separate rows.
Using prioritized risks
Management may decide to target, say, the top 5% of risks initially. This is an arbitrary value that can be reviewed/adjusted later.
Following the FMEA method, the risks are assessed, RPNs calculated and then risks are ranked by RPN.
5% of 1000 (the maximum RPN value) is 50. So any RPN above 50 requires review and (probably) control improvements.
All risks with RPNs above 50 are identified as "HIGH RISK". This criterion is of course based on the arbitrary 5% value noted above.
If the organization is well controlled with relatively few HIGH RISK items, the 5% value may be extended to, say 15% to address lower risks.
Alternatively, if there are simply too many HIGH RISK items to tackle at once, they may be addressed in top-down sequence according to the RPNs.
The prioritized list of risks provides management with a rational basis for determining how much resource to apply to risk reduction: the cutoff point should go further down the list if more resources are allocated, and vice versa.

## FMEA Sample
A/A | Asset Name | Function | Potential Vulnerability | Potential Threat | Potential Business Consequence (Impact) | Impact | Likelihood | Current Controls |  | Vulnerability | RPN
[8 empty] | Preventive Controls | Detective Controls
1 | Medical Clinic Employee Data | Employees information | Database not encrypted | Insider Employee gets employee personal data | Disclosure or modification of personal information | 8 | 6 | Internal Employee Rules and Procedures available | Log Monitoring | 6 | 288
2 | Medical Clinic Employee Data | Employees information | Backup not configured | Critical data loss | Clinic loses employee information. Availability is impacted until they can be created anew. | 8 | 3 | Keep backup compatible with 3-2-1 backup rule. | Database log monitoring | 3 | 72
3 | Medical Clinic Employee Data | Employees information | Employees' passwords are not salted | Rainbow table attack | Disclosure or modification of personal information | 8 | 2 | Salt passwords along hashing |  | 5 | 80
4 | Medical Clinic Financial Data | Contains information about the clinic's financial activities | Backup not configured | Critical data loss | Loss of critical financial transactions' receipts | 6 | 4 | Keep backup compatible with 3-2-1 backup rule. | Database log monitoring | 5 | 120
5 | Medical Clinic Financial Data | Contains information about the clinic's financial activities | Database not encrypted | Insider Employee/ Competitor gets clinic's financial data | Disclosure or modification of financial and potentially personal data (concerning patients) | 8 | 7 | 1) Use a database encryption tool. 2) Grant access based on strict user requirements | Log Monitoring | 7 | 392
6 | Patient Medical Data | Patients' medical information | Backup stored in the same location as original/Backup not configured | Destruction (e.g. hardware overheat) of original data or backup data may result in total loss of all data | Violation of GDPR. Impact on clinic's reputation. Patient treatmnets affected | 9 | 4 | Keep backup compatible with 3-2-1 backup rules and in different storage device . | Database Log Monitoring | 8 | 288
7 | Patient Medical Data | Patients' medical information | Database is not encrypted | Insider Employee gets/changes patients' medical data | Violation of medical confidentiality. Impact on clinic's reputation. Patient treatmnets affected | 10 | 8 | Internal Employee Rules and Procedures available | Log monitoring | 8 | 640
8 | Patient Personal Data | Patients' personal information | Database is not encrypted | Attacker/Insider employee (with unauthorised access), can view raw patient data | Violation of GDPR rules and financial impact via imposed fines | 9 | 8 | 1) Use a database encryption tool. 2) Grant access based on strict user requirements | Log monitoring | 8 | 576
9 | Patient Personal Data | Patients' personal information | Backup not configured | Critical data loss | Clinic loses patients' personal information. Availability is impacted until they can be created anew./Impact on clinic reputation. | 9 | 4 | Keep backup compatible with 3-2-1 backup rule. | Database Log Monitoring | 8 | 288
10 | Patient Admission | Process that dictates the steps required for a patient to be admitted to the clinic | Insufficient checks before admitting patient | Medical Identity Theft | Perpetrator gains admission to the clinic and its facilities | 7 | 3 | Stricter checks of client information before admitting patients |  | 6 | 126
11 | Patient Monitoring | Process that describes how a patient's treatment should be carried out and how to monitor their health during their stay at the clinic | Data inputs are not sufficiently checked | User mistakes inputs | Patient treatmnets affected. Impact on clinic's reputation | 9 | 6 | Check input integrity |  | 6 | 324
12 | Patient Monitoring | Process that describes how a patient's treatment should be carried out and how to monitor their health during their stay at the clinic | No network connection | Network failure interrupts process. Patients' medical data is not accessible and cannot be modified | Patient treatmnets affected. Impact on clinic's reputation | 10 | 2 |  |  | 6 | 120
13 | Payroll Process | Process that describes how employees' payroll should be processed. | Payroll software parameters have not been properly set | Susceptible to Payroll Fraud e.g. Time Theft | Financial losses and incosistencies in financial data | 7 | 4 | Payroll software parameters checked on regular basis. |  | 4 | 112
14 | Supply Of Drugs | The process during which: 1) drug deficiences are found and, 2) corresponding orders are made to the suppliers | No network connection | Network failure interrupts process, order is not completed and data is lost | Clinic suffers drug deficiencies | 7 | 2 | Save data locally to be retrieved and finish process when network connection is restored | Notify users when the process has been interrupted and not completed successfully | 2 | 28
15 | Windows Server 2012 R2 | Operation System used in clinic's servers | CVE-2021-34527 Windows Print Spooler Remote Code Execution Vulnerability | Remote code execution | Priviledge escalation & unauthorized access | 8 | 6 | Install latest software patches | Log Monitoring | 4 | 192
16 | Windows Server 2012 R2 | Operation System used in clinic's servers | Scripting Engine Memory Corruption Vulnerability CVE-2020-0674 | Remote code execution | Priviledge Escalation causing system malfunction | 8 | 6 | Install latest software patches |  | 4 | 192
17 | Windows Server 2012 R2 | Operation System used in clinic's servers | EternalBlue | Attacker can execute code remotely | Data corruption and denial of access | 9 | 6 | Install latest software patches |  | 4 | 216
18 | Windows Vista Service Pack 2 | Operation System used in clinic's workstations | Product support has ended | Attacker installs malware | Data confidentiality compromised and possible system malfuntion | 8 | 7 | Grant access only to specific websites, avoid downloads and minimize internet use in general | Check for suspicious traffic in the network | 7 | 392
19 | WIFI Access Point | Allows devices to connect wirelessly to the clinic's network | Default password still in use / Not using advanced wireless security (e.g. WPA2 - Enterprise) | Unauthorized access to the network | Network traffic intercepted by unauthorised user. Potential data breach | 6 | 8 | Change default password and configure WPA2-Enterprise security | Monitor active connections | 5 | 240
20 | WIFI Access Point | Allows devices to connect wirelessly to the clinic's network | Duplicate SSIDs are permitted | Evil Twin attack | Attacker intercepts connected user's credentials and data | 7 | 4 | Deploy WIPS (Wireless Intrusion Prevention System) |  | 7 | 196
21 | Firewall & Router | A device that connects various subnets and routes traffic | Inadequate firewall rules | DoS attack | Subnets cannot communicate with each other. Availability of services may be affected | 10 | 5 | During firewall Setup: 1) Implement narrow permissions and widen later if required. 2) Disable firewall ports and adequatly protect the ones that have to stay open | Log Monitoring | 6 | 300
22 | Firewall & Router | A device that connects various subnets and routes traffic | Depreciated Software (4.3.8 and prior) | Remote attacker executes arbitary code | System Compromise: Remote attackers can gain control of the system | 10 | 3 | Upgrade to the latest version of FortiOS, recommended by FortiGuard | Log Monitoring | 6 | 180
23 | Insulin pump | A device that monitors sugar levels and delivers insulin to the patient when necessary | Remote connection enabled | Attacker can connect to device via bluetooth | Attacker controls insulin dosage and can cause physical harm | 8 | 2 | Disable remote control of device |  | 7 | 112
24 | Vital Signs Monitor | Device that monitors the patient's vital signs | Software hasn't been updated (URGENT/11) | Remote Code Execution | Attacker takes complete control of device | 10 | 2 | Immediately install latest software patches | Medical personnel needs to validate device output | 7 | 140
25 | Main Router | packet filtering , routing packages | incomplete package sender authentication | access to the network of unauthorized user | non authorised users send or receive confidential data | 8 | 4 | Mandatory Access Control | Log Monitoring | 4 | 128
26 | Main Router | packet filtering , routing packages | Not properly configured packet filtering | DDoS attack overwhelms router | Inability to access the internet | 10 | 6 | Filter incoming traffic | Log monitoring | 4 | 240
27 | Main Router | packet filtering , routing packages | Default router credentials | Unauthorized access to router configurations | Network malfunctions | 9 | 6 | Change default router credentials |  | 6 | 324
28 | Secretariat Server | Server which contains employees', payroll and patients' personal information, as well as software to complete the clinic's various responsibilities | Active Directory not properly configured | Certain data is accessible by unauthorized employees | Data leaks or corruption of important information | 7 | 8 | Configure Active Directory | Log Monitoring | 6 | 336
29 | Secretariat Server | Server which contains employees', payroll and patients' personal information, as well as software to complete the clinic's various responsibilities | Firewall rules not configured for Remote Desktop | Attacker connects remotely to server | Unauthorized access to server | 10 | 6 | Configure Firewall rules for Remote Desktop | Log Monitoring | 7 | 420
30 | Server A & B | Database servers containing patients' medical information | SQL input is not sanitized | SQL Injection | Disclosure of patient data and database corruption | 10 | 5 | Sanitizing Input fields |  | 7 | 350
31 | Server A & B | Database servers containing patients' medical information | Weak password used for login | Brute force attacks can crack the password | Attacker gains root access to server | 10 | 7 | Use SSH keys instead of conventional password | Log Monitoring | 6 | 420
32 | Server A & B | Database servers containing patients' medical information | No backup server available | Service not working due to hardware (e.g. overheat) or software failure | Server is down, patients' medical data is unavailable. Vital business processes cannot be conducted | 10 | 4 | 1)Deploy a remote backup server 2) Ensure room temperature is ideal for hardware - install Air-condition system | Keep-alive pings | 5 | 200
33 | Switch | Connects the devices in a specific subnet | Unstable External Power Supply | Switch is damaged due to power failure | Switch is out and sub-network is disconnected | 9 | 3 | Add a voltage regulator device (controlls power supply) |  | 3 | 81
34 | Switch | Connects the devices in a specific subnet | Port security not configured | MAC flooding attack | Data sent inside a VLAN is visible to anyone inside the network | 7 | 3 | Configure Port Security | Sniffing network packages/ Network monitoring | 6 | 126
35 | Medical Stuff Tablet | A portable device that allows the clinic's personnel to monitor the patients | Device uses a SIM card | SIM swapping | Attacker bypasses services that require 2FA | 2 | 3 | Agree on certain security steps to be followed during transactions between clinic's authorized personnel and provider |  | 2 | 12
36 | Medical Stuff Tablet | A portable device that allows the clinic's personnel to monitor the patients | Portability and absent or not strong authentication | Tablet is misplaced and lost | Patients' personal data gets leaked or corrupted | 7 | 5 | Use strong passwords that are changed regularly | Gps and lost device location enabled | 5 | 175
37 | Medical Stuff Tablet | A portable device that allows the clinic's personnel to monitor the patients | Access to the internet is not restricted | Unintentionally install malware | Attacker gains access to confidential data | 8 | 3 | 1) Install trusted antivirus software 2) Avoid visiting and downloading from untrusted websites | Check for suspicious traffic in the network | 4 | 96
38 | Admin Terminal | Computer used by the system administrator | Weak password used for login | Unauthorized access | Patients' medical data gets leaked or corrupted | 10 | 5 | Use strong passwords that are changed regularly | Log Monitoring | 6 | 300
39 | Reception /Secretary Workstation | Desktop computer used by reception employees | E-mails not filtered | Spear-Phising attacks | Data leak and system malfunction | 8 | 7 | Filtering of emails |  | 6 | 336
40 | Reception/ Secretary Workstation | Desktop computer used by reception employees | Workstations are easily accessible by unauthorized personnel and clients | Unauthorized access to workstation | Disclosure or modification of information about the business and the patients | 8 | 3 | 1)Change physical location of computer 2) Strong user passwords 3) Change passwords on regular basis | Monitoring System for checking who accesses the reception/secretary room | 6 | 144
Note on C2: List down the fucntion or purpose of the asset. If more than one purpose is identified for the identified service list them down separately
Note on D2: In what all ways the service running on this asset can fail? ie the vulnerabilities List down each failure mode separately
Note on E2: if the vulnerability happens, then what could be the effect of the failure? If there is more than one failure list them seperately
Note on G2: Refer Severity Table
Note on H2: Refer Probabilty Table
Note on I2: Identify the current controls vis a vis preventive and detective controls. If there are more than one, then list them separately
Note on K2: Refer Detection table

## Impact
Effect | Impact of Threat realisation | Ranking
Catastrophic | Resource not available / Problem unknown | 10
Extreme | Resource not available / Problem known and cannot be controlled | 9
Very High | Resource not available / Problem known and can be controlled | 8
High | Resource Available / Major violation of policies | 7
Moderate | Resource Available / Major violations of process | 6
Low | Resource Available / Major violations of procedures | 5
Very Low | Resource Available / Minor violations of policies | 4
Minor | Resource Available / Minor violations of process | 3
Very Minor | Resource Available / Minor violations of procedures | 2
None | No effect | 1

## Likelihood
PROBABILITY of Failure | Failure Prob | Ranking
Very High: Threat is almost inevitable | >1 in 2 | 10
| 1 in 3 | 9
High: Repeated Threat occurences | 1 in 8 | 8
| 1 in 20 | 7
Moderate: Occasional Threat occurences | 1 in 80 | 6
| 1 in 400 | 5
| 1 in 2,000 | 4
Low: Relatively few Threat occurences | 1 in 15,000 | 3
| 1 in 150,000 | 2
Remote: Threat occurence is unlikely | <1 in 1,500,000 | 1

## Vulnerability
Vulnerability | Ranking
The vulnerability is very exposed and directly, remotely exploitable, and its exploitation could result in severe impacts. Relevant security control or other remediation is not implemented and not planned; or no security measure can be identified to remediate the vulnerability. | 10
The vulnerability is exposed and exploitable, and its exploitation could result in severe impacts. Relevant security control or other remediation is not implemented and not planned; or no security measure can be identified to remediate the vulnerability. | 9
The vulnerability is of very high concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is planned but not implemented | 8
The vulnerability is of high concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is planned but not implemented | 7
The vulnerability is of moderate concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is partially implemented and somewhat effective. | 6
The vulnerability is of moderate concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is implemented and effective. | 5
The vulnerability is of minor concern, but effectiveness of remediation could be improved. Relevant security control or other remediation is fully implemented and somewhat effective | 4
The vulnerability is of minor concern, but effectiveness of remediation could be improved. Relevant security control or other remediation is fully implemented and effective | 3
The vulnerability is not of concern. Relevant security control or other remediation is fully implemented, assessed, and effective | 2
There is no vulenrability | 1